## Risk Register
Risk ID | Risk Description | Category | Likelihood (1-3) | Impact (1-3) | Severity Score | Risk Owner | Status | Mitigation Plan | Target Date | Last Reviewed
R-001 | MFA is not enforced for all administrative accounts | Identity | 3 | 3 |  | IT Manager | Mitigating | Enforce MFA org-wide for all admin roles; track exceptions by name | 2026-08-15 | 2026-07-01
R-002 | No tested incident response plan exists | Governance | 2 | 3 |  | CISO / Security Lead | Open | Draft IR plan and run a tabletop exercise with leadership | 2026-09-01 | 2026-07-01
R-003 | Key vendor with access to customer PII lacks SOC 2 report | Third-Party Risk | 2 | 3 |  | Procurement | Open | Request SOC 2 report; add right-to-audit clause at renewal | 2026-10-01 | 2026-07-01
R-004 | Cloud storage bucket permissions are not reviewed on a schedule | Cloud Security | 2 | 2 |  | Cloud Engineering | Mitigating | Enable CSPM alerting; add quarterly manual review | 2026-08-01 | 2026-07-01
R-005 | Departing employee access is not consistently revoked same-day | Identity | 2 | 2 |  | HR / IT | Open | Automate deprovisioning via HRIS-triggered workflow | 2026-09-15 | 2026-07-01
R-006 | Backup restore process has not been tested in over a year | Resilience | 1 | 3 |  | IT Manager | Open | Schedule quarterly restore drills; document results | 2026-08-30 | 2026-07-01

## Scoring Legend
Field | Value | Definition
Likelihood | 1 | Unlikely — no known precedent, would require unusual circumstances
Likelihood | 2 | Possible — plausible within the next 12 months given current controls
Likelihood | 3 | Likely — expected to occur without intervention, or has occurred before
Impact | 1 | Minor — limited operational disruption, no material financial or reputational harm
Impact | 2 | Moderate — meaningful disruption, contained financial or reputational impact
Impact | 3 | Severe — significant financial, legal, regulatory, or reputational consequences
Severity Score | 1-2 (Low) | Monitor; revisit at next quarterly review
Severity Score | 3-4 (Moderate) | Assign owner and mitigation plan within 90 days
Severity Score | 5-7 (Elevated) | Assign owner and mitigation plan within 30 days
Severity Score | 8-9 (Critical) | Escalate immediately; executive visibility required